## Project Planner
Project Planner
[5 empty] | Period Highlight: | 8 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (WEEKS) | [11 empty] | Sem 1 end |  |  | Sem 2 start | [11 empty] | end
[6 empty] | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Tasks | bar: Sem 1 end 15; Sem 2 start 18; end 30
Programming language / ide selection | 3 | 1 | 3 | 1 | 100%
App testing methodology | 3 | 1 | 3 | 1 | 100%
Set up GitHub. | 3 | 1 | 3 | 1 | 100%
Set up client / server sockets. | 4 | 1 | 4 | 5 | 100%
Set up encryption protocol (AES or RES 256) | 5 | 1 | 4 | 5 | 100%
Set up/design database on server. | 6 | 1 | 4 |  | 50%
Initial login page creation and functionality | 7 | 1 |  |  | 0%
Registration page creation and functionality | 8 | 1 |  |  | 0%
Home ui creation and page navigation | 9 | 1 |  |  | 0%
Feature 1 design. | 10 | 1 |  |  | 0%
Feature 1 development | 11 | 3 |  |  | 0%
Feature 2 design. | 14 | 1 |  |  | 0%
Feature 2 development | 15 | 3 |  |  | 0%
Feature 3 design. | 18 | 1 |  |  | 0%
Feature 3 development | 19 | 3 |  |  | 0%
Feature 4 design. | 22 | 1 |  |  | 0%
Feature 4 development | 23 | 3 |  |  | 0%
Reports and Presentations
Project proposal Draft | 4 | 3 | 4 | 5 | 100%
Project proposal | 4 | 5 | 4 | 5 | 100%
Progress report draft | 10 | 4
Progress report | 10 | 6
Progress oral | 10 | 6
Project update draft | 18 | 4
Project update | 18 | 6
Final report draft | 25 | 5
Final report | 25 | 6
Final Oral | 25 | 6